## Smartsheet Project
Task Name | Start | Finish | Assigned To | Duration | Predecessors | Status | Comments
Product Increment 1 | 2018-10-01 | 2018-10-31 |  | 23d
Create movable player | 2018-10-01 | 2018-10-08 |  | 6d
Create hand mechanic | 2018-10-01 | 2018-10-08 |  | 6d
Design basic level | 2018-10-01 | 2018-10-15 |  | 11d
Implement basic physics | 2018-10-08 | 2018-10-15 |  | 6d
Research advanced physics | 2018-10-01 | 2018-10-08 |  | 6d
Implement advanced physics as applicable to first level | 2018-10-08 | 2018-10-15 |  | 6d
Create scene shell | 2018-10-01 | 2018-10-08 |  | 6d
play-test level | 2018-10-15 | 2018-10-22 |  | 6d
Correct bugs | 2018-10-22 | 2018-10-25 |  | 4d
Release version 1 | 2018-10-29 | 2018-10-31 |  | 3d
Research multiplayer | 2018-10-15 | 2018-10-22 |  | 6d
design overarching gameplay roadmap | 2018-10-08 | 2018-10-15 |  | 6d
Basic game design document | 2018-10-01 | 2018-10-15 |  | 11d
Proof of Concept design | 2018-10-15 | 2018-10-22 |  | 6d
Design basic game mechanics | 2018-10-01 | 2018-10-01 |  | 1d
Product Increment 2 | 2018-11-01 | 2018-11-30 |  | 22d
Multiplayer implementation | 2018-11-01 | 2018-11-15 |  | 11d
Placeholder Assets | 2018-11-01 | 2018-11-15 |  | 11d
Improved AI | 2018-11-01 | 2018-11-15 |  | 11d
Testing | 2018-11-15 | 2018-11-29 |  | 11d
Final/Tentative Menu Implementation | 2018-11-01 | 2018-11-02 |  | 2d
Player testing | 2018-11-15 | 2018-11-22 |  | 6d
release version 2 | 2018-11-29 | 2018-11-30 |  | 2d
Proof of Concept Implementation | 2018-11-01 | 2018-11-15 |  | 11d
Product Increment 3 | 2018-12-01 | 2018-12-20 |  | 15d
Adaptations from player testing | 2018-12-01 | 2018-12-14 |  | 11d
Implement full level set (3 levels in 1 world) | 2018-12-01 | 2018-12-13 |  | 10d
Design additional level sets | 2018-12-01 | 2018-12-14 |  | 11d
test full level-set | 2018-12-14 | 2018-12-17 |  | 2d
Revise/Finalize poster board | 2018-12-14 | 2018-12-20 |  | 5d
Design poster board | 2018-12-01 | 2018-12-14 |  | 11d
Design additional game mechanics | 2018-12-01 | 2018-12-14 |  | 11d
release version 3 | 2018-12-14 | 2018-12-14 |  | 1d
Poster board demo | 2018-12-20 | 2018-12-20 |  | 1d
Product Increment 4 | 2019-01-01 | 2019-01-18 |  | 14d
formalize adaption from player testing | 2019-01-01 | 2019-01-04 |  | 4d
implement changes from adapation | 2019-01-04 | 2019-01-15 |  | 8d
release version 4 | 2019-01-17 | 2019-01-18 |  | 2d
test changes from adaption | 2019-01-15 | 2019-01-17 |  | 3d
Product Increment 5 | 2019-02-01 | 2019-02-04 |  | 2d
release version 5 | 2019-02-01 | 2019-02-01 |  | 1d
further adaptations and testing | 2019-02-02 | 2019-02-04 |  | 2d
Product Increment 6 | 2019-03-01 | 2019-03-01 |  | 1d
release final version (6) | 2019-03-01 | 2019-03-01 |  | 1d